## Sheet1
Task | Owner | Start Date | End Date | Status | Comments
Define project scope | Shivam Patel | 2024-09-02 | 2024-09-06 | Complete | Scope finalized in Overleaf report
Design database schema | Shivam Patel | 2024-09-09 | 2024-09-13 | In Progress | ER diagram drafted
Build ETL pipeline | Shivam Patel | 2024-09-16 | 2024-09-27 | Pending | ETL scripts to be written in Python
Create dashboards | Shivam Patel | 2024-09-30 | 2024-10-04 | Pending | Will use Dash for interactivity
Test and document system | Shivam Patel | 2024-10-07 | 2024-10-11 | Pending | To run tests and finalize PDF
Submit final report | Shivam Patel | 2024-10-14 | 2024-10-18 | Pending | Final submission including code